## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | Customers sign up for the newsletter on the tablets | 78% of the customers signed up for the newsletter on the tablets | Continue to survey consistently and monitor results for additional improvements
Customers | Went well | Ease of check out process | 82% of the customers found the checkout process quick, easy, and secure | Continue to survey consistently and monitor results for additional improvements
Customers | Went well | On a scale of 1-5, customers rating of their dining experience with the tablet overall | 40% of guests rated their experience as a 4 out of 5 | Work on the areas where customer experience could be improved: increased order accuracy, reduced lobby wait time, reduced technical issues with the tablets etc
Customers | Needs improvement | Interaction with tablets | 12% of customers experienced technical issues with the tablets | Resolve any technical issues encountered during the POS integration process and update the process manual so that the solution is easy to find next time that issue comes up
Customers | Needs improvement | Order accuracy from the kitchen | 28% of customers reported that their orders were incorrect | Check for the technical issues that’s affecting ticket accuracy
Customers | Needs improvement | Lobby wait time | 54% of customers reported they waited for more than 15mins to get a table | Research on what could be done to decrease the wait time
Project team | Went well | Tablets Usage | Guests seemed to get the hang of the tablets | Continue to survey consistently and monitor results for additional improvements
Project team | Went well | Ticket flow was smooth | Tickets were easy to track and came through at a good pace | Continue to survey consistently and monitor results for additional improvements
Project team | Went well | Working of tablets and their installation | Tablets installed and working at my location | Continue to survey consistently and monitor results for additional improvements and resolve any technical issues that might be encountered
Project team | Needs improvement | Table turn time | One area we could still improve is table turn time. We didn’t see as much of a decrease as we wanted to in that area. | Research on what could be done to decrease the table turn time
Project team | Needs improvement | Order returns | But even though the ticket flow was smooth, there were still orders that got sent back. So, that’s still an issue that needs to be addressed. Not as many as before, but there were still some food orders that got sent back. | Implementing more updates to kitchen operations as a result of the new ticket flow
Project team | Needs improvement | Participation in Birthday club | We didn’t get many participants for the birthday club though | Research and proactively work to grow the participant list