## Slide 1
Stakeholder | Role | Power (H/M/L) | Interest (H/M/L) | Notes
Omar Mubarak | Owner | H | L | Communicate regularly, but not daily. Give updates on progress and performance so as to keep them satisfied but not overburden with project communications.
Deanna Coleman | Director of Operations | H | H | Communicate daily by managing closely and make every effort to fully engage with them
Carter Ward | Executive Chef | H | L | Keep updated on progress to inform and get feedback regarding issues that concern the kitchen staff, or to finalize menu choices
Gilly Tyson | General Manager (North) | M | M | Communicate as needed to inform and get feedback on training and providing input on general restaurant operations
Alex Schmidt | General Manager (Downtown) | M | M | Communicate as needed to inform and get feedback.
Nia Williams | General Manager (Waterfront) | L | L | Not directly involved, but should be updated after we try to scale the tablet program to this location in the future.
Zane Dutchman | Kitchen Manager (North) | L | M | Communicate as needed on progress and to inform and get feedback regarding issues that concern the kitchen staff.
Larissa Stein | Kitchen Manager (Downtown) | L | M | Communicate as needed on progress and to inform and get feedback regarding issues that concern the kitchen staff.
Seydou Diallo | Restaurant Technology Consultant | L | H | Keep them adequately informed where required like for designing and implementing appropriate solutions wrt technology, software etc and to ensure that no major issues are arising
Stakeholder Analysis

## Slide 2
Keep satisfied (high priority)
Manage closely (high effort)
Monitor (minimum effort)
Show consideration
Power
high
low
med
high
low
Omar
Owner
Drag each stakeholder’s box to the appropriate place on the power-interest grid
Deanna
Director of Operations
Carter
Exec. Chef
Gilly
GM - North
Alex
GM - Downtown
Zane
Kitchen Manager - North
Larissa
Kitchen Manager - Downtown
Seydou
Restaurant Consultant
Interest
med
Nia
General Manager - Waterfront